Project Implementation Plan, Sprint Plan, RACI and Milestones

Document ID: DT-GUARDIAN-PROJECT-025
Version: 1.0
Document Status: Draft for Founder, Product, Vendor, Engineering, QA, Security, Privacy and Commercial Review
Prepared For: Druvatara
Prepared By: Founder Office / Product Management / Programme Management
Product: Druvatara Guardian

Primary Delivery Strategy: Android First → Commercial Android → iOS POC → Commercial iOS
Project Model: Milestone-Based Product Development
Primary Launch Market: India
Confidentiality Classification: Strictly Confidential and Proprietary
Document Date: August 10, 2026

Document Control

| Field | Information |
| --- | --- |
| Document Name | Project Implementation Plan, Sprint Plan, RACI and Milestones |
| Document ID | DT-GUARDIAN-PROJECT-025 |
| Version | 1.0 |
| Product Owner | Founder and Chief Executive Officer, Druvatara |
| Programme Owner | Founder Office / To be assigned |
| Vendor Project Manager | To be assigned |
| QA Owner | To be assigned |
| Security Owner | To be assigned |
| Primary Audience | Founder, Development Companies, Project Managers, Product Managers, Engineering Leads, QA, Security, Privacy, DevOps, Commercial Teams and Procurement |
| Current Status | Draft |
| Preceding Document | DT-GUARDIAN-ADMIN-024 – Administrative Portal Functional and Technical Specification |
| Next Document | DT-GUARDIAN-CODE-026 – Source Code, Repository, Coding Standards, OSS and SBOM Specification |

Revision History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 1.0 | August 10, 2026 | Druvatara Founder Office | Initial comprehensive implementation roadmap and responsibility model |

1. Purpose

This document defines how Druvatara Guardian shall be executed as a development project.

The previous documents define:

- What Guardian is.

- what features must exist.

- how Android and iOS differ.

- backend architecture.

- security.

- privacy.

- billing.

- TARA.

- operations.

- testing.

This document converts those requirements into:

- Delivery phases.

- workstreams.

- sprints.

- technical gates.

- milestones.

- responsibilities.

- dependencies.

- acceptance criteria.

- project governance.

- commercial payment gates.

- launch readiness.

2. Primary Project Objective

Deliver a production-capable Druvatara Guardian platform in a controlled sequence:

PRODUCT FOUNDATION

↓

ANDROID TECHNICAL FOUNDATION

↓

ANDROID MVP

↓

ANDROID BETA

↓

ANDROID COMMERCIAL RELEASE

↓

iOS TECHNICAL POC

↓

iOS PRODUCTION BUILD

↓

iOS COMMERCIAL RELEASE

↓

STABILISATION + HANDOVER

3. Core Delivery Principle

Druvatara shall not attempt to build every planned Guardian capability simultaneously.

The project shall prioritise:

- Core architecture.

- Android MVP.

- real-device reliability.

- backend/security.

- commercial Android.

- iOS feasibility.

- iOS commercial parity where platform permits.

- advanced roadmap features later.

4. Project Success Definition

The project is successful only when:

- Contracted Feature IDs work.

- backend and mobile integrate.

- real devices enforce policy.

- Android survives realistic background conditions.

- iOS uses Apple-supported architecture.

- family isolation is secure.

- privacy controls work.

- billing is verified server-side.

- admin operations are controlled.

- UAT passes.

- stores accept the production build.

- source code and accounts belong to Druvatara.

- handover is complete.

5. Project Non-Goals

The initial project shall not attempt to deliver:

- Full UEM.

- Windows.

- macOS.

- Linux.

- ChromeOS.

- remote wipe.

- enterprise kiosk.

- USB/Bluetooth enterprise restrictions.

- hidden surveillance.

- private-message interception.

- grooming AI in production.

- intimate-media cloud processing.

- self-harm diagnosis.

- enterprise multi-tenancy.

These remain future programmes unless separately contracted.

6. Delivery Methodology

Recommended methodology:

Agile delivery with milestone-controlled acceptance.

Use:

- 2-week development sprints.

- weekly progress review.

- sprint demo.

- QA within each sprint.

- formal milestone acceptance.

- change-control process.

7. Recommended Sprint Duration

Standard:

2 weeks

A sprint shall contain:

- Planning.

- implementation.

- code review.

- developer testing.

- QA handoff.

- demo.

Critical defects may continue across the next sprint but must remain tracked.

8. Recommended Overall Programme Structure

The complete project may be divided into:

Phase 0

Project mobilisation and technical validation.

Phase 1

Design and platform foundation.

Phase 2

Android MVP.

Phase 3

Android advanced/commercial capabilities.

Phase 4

Android beta and hardening.

Phase 5

Android commercial launch.

Phase 6

iOS feasibility POC.

Phase 7

iOS implementation.

Phase 8

iOS beta/commercial launch.

Phase 9

Final stabilisation and handover.

9. Indicative Programme Duration

A realistic professionally staffed programme should be estimated by vendors rather than dictated solely by calendar targets.

For procurement comparison, Druvatara may request quotations using an indicative programme of approximately:

24–32 weeks for Android-first commercial delivery plus iOS production follow-on, depending on:

- Team size.

- entitlement approvals.

- Play policy reviews.

- defect volume.

- native Android complexity.

- iOS Family Controls feasibility.

- external provider integrations.

- store review.

This is a planning baseline, not a vendor guarantee.

10. Minimal-Team Reality

If Druvatara chooses an extremely small team:

- one developer.

- founder product owner.

- one tester.

The timeline will increase materially.

The architecture and scope should not be reduced dishonestly merely to fit an unrealistic deadline.

11. Recommended Delivery Team

Minimum professional vendor team:

| Role | Suggested Allocation |
| --- | --- |
| Project Manager / Scrum Lead | 0.5–1 |
| Product/Business Analyst | 0.5 |
| UI/UX Designer | 0.5–1 early phase |
| Flutter Developer | 1–2 |
| Android Native Developer | 1 |
| iOS Native Developer | 1 during iOS phase |
| Backend Developer | 1–2 |
| QA Engineer | 1–2 |
| DevOps Engineer | 0.25–0.5 |
| Security Reviewer | Milestone-based |
| AI Engineer | 0.25–0.5 during TARA phase |

The same person may hold multiple roles in a smaller engagement, but responsibilities remain separate.

12. Druvatara Internal Roles

Recommended Druvatara-side roles:

- Founder / Executive Sponsor.

- Product Owner.

- Technical Advisor / Architect.

- QA/UAT owner.

- Privacy/Security reviewer.

- Commercial/contract reviewer.

Initially, the Founder may hold several of these roles.

13. Workstreams

Project work shall be divided into:

WS-01 Product & Requirements

WS-02 UI/UX

WS-03 Flutter Shared Application

WS-04 Android Native

WS-05 iOS Native

WS-06 Backend/API

WS-07 Database

WS-08 TARA/AI

WS-09 Admin Portal

WS-10 DevOps

WS-11 QA

WS-12 Security & Privacy

WS-13 Compliance & Store Launch

WS-14 Commercial/Billing

WS-15 Documentation & Handover

14. Phase 0 – Project Mobilisation

Indicative Duration: 1–2 weeks

Objectives:

- Contract finalisation.

- scope baseline.

- technical POCs.

- development environment.

- repositories.

- access.

- design kickoff.

15. Phase 0 Deliverables

Required:

- Signed scope baseline.

- included Feature IDs.

- excluded Feature IDs.

- vendor assumptions.

- development team.

- project calendar.

- repositories.

- coding workflow.

- development environments.

- communication channels.

- risk register.

- architecture review.

- Android POC list.

- iOS entitlement request plan.

16. Gate M0 – Project Start Approval

Druvatara approves mobilisation only when:

[ ] Contract signed

[ ] NDA/IP terms signed

[ ] Feature IDs baselined

[ ] Repository ownership confirmed

[ ] Cloud ownership confirmed

[ ] Team confirmed

[ ] Sprint plan confirmed

[ ] Access model confirmed

17. Phase 1 – Product and Design Foundation

Indicative Duration: 2–4 weeks, partly parallel with engineering foundation.

Scope:

- Final UX flows.

- design system.

- technical architecture refinement.

- API contracts.

- DB schema baseline.

- Android application skeleton.

- backend skeleton.

- admin skeleton.

18. Design Deliverables

Required Figma coverage for P0:

- Parent onboarding.

- registration.

- family creation.

- child creation.

- pairing.

- child setup.

- permission screens.

- dashboard.

- screen time.

- app control.

- schedules.

- requests.

- Web Safety.

- device health.

- alerts.

19. Design Approval Rule

No production implementation of major feature shall proceed indefinitely on unapproved wireframes.

Status:

WIREFRAME

DESIGN REVIEW

APPROVED

IMPLEMENTATION

20. Sprint 1 – Engineering Foundation

Typical objectives:

Backend

- NestJS project.

- environment config.

- PostgreSQL.

- Prisma.

- auth foundation.

- health endpoint.

Mobile

- Flutter project.

- routing.

- environment configuration.

- design-system baseline.

DevOps

- dev environment.

- CI.

- code quality.

21. Sprint 1 Acceptance

Must demonstrate:

- Parent app launches.

- backend responds.

- CI passes.

- DB migration runs.

- environment secrets not committed.

- one authenticated skeleton endpoint.

22. Sprint 2 – Account and Family

Scope:

- Registration.

- verification.

- login.

- family creation.

- child profile.

- session management.

Feature groups:

- AUTH.

- FAM.

- CHILD.

23. Sprint 2 Demo

Vendor demonstrates:

Register

→ Verify

→ Login

→ Create Family

→ Add Child

Real backend only.

No mocked production flow accepted as completion.

24. Sprint 3 – Pairing and Device Identity

Scope:

- Pairing sessions.

- QR.

- seven-digit code.

- child device registration.

- device credential.

- device heartbeat.

- secure pairing.

25. Sprint 3 Technical Gate

Mandatory security tests:

- Expired code.

- reused code.

- second-family use.

- duplicate registration.

- device revocation.

26. Sprint 4 – Android Permissions and Device Health

Scope:

- Usage Access.

- notification.

- battery guidance.

- location foundation.

- VPN consent foundation.

- device-health engine.

- status reporting.

27. Android Native Foundation

Kotlin modules should now exist:

DeviceIdentityManager

PermissionManager

CapabilityManager

DeviceHealthManager

PolicySyncManager

LocalStorage

SyncWorker

BootRecovery

28. Sprint 5 – Usage and Screen Time

Scope:

- Usage collection.

- daily counter.

- per-app usage.

- daily limits.

- warnings.

- local counters.

- parent UI.

29. Sprint 5 Acceptance Scenario

Mandatory:

Parent sets 60 minutes

↓

Child usage tracked

↓

Warning

↓

60 minutes reached

↓

Restriction behaviour activates

30. Sprint 6 – Application Control

Scope:

- App inventory.

- app search.

- allow/block rule.

- essential apps.

- per-app limit.

- policy sync.

Conditional sensitive Android methods require approved design.

31. Sprint 6 Gate

Vendor must document actual Android behaviour across:

- Pixel.

- Samsung.

- one Xiaomi/Redmi device.

No claim of universal app blocking without evidence.

32. Sprint 7 – Schedules and Requests

Scope:

- Bedtime.

- School Time.

- custom schedule.

- overnight schedules.

- temporary grants.

- child request.

- parent approval/rejection.

33. Sprint 7 Offline Test

Mandatory:

- Device disconnected.

- schedule activates.

- screen-time restriction works.

- existing temporary grant expires correctly.

34. Sprint 8 – Web Safety

Scope:

- Android VpnService.

- local rules.

- domain allow/block.

- category lookup.

- threat reputation.

- health.

35. Web Safety POC Gate

Before full rollout, demonstrate:

- VPN permission.

- browsing allowed.

- blocked domain.

- network transition.

- competing VPN state.

- child device reboot.

- battery impact baseline.

36. Sprint 9 – Alerts and Notifications

Scope:

- alert engine.

- alert list.

- FCM.

- child request push.

- protection-health push.

- privacy masking.

- notification centre.

37. Sprint 10 – Location and Geofencing

Scope:

- Latest location.

- freshness.

- parent map.

- background location.

- safe zones.

- entry/exit.

- debounce/hysteresis.

38. Location Privacy Gate

No milestone acceptance until:

- stale location represented.

- co-parent restrictions planned.

- exact coordinates absent from push.

- location access correctly authorised.

- retention configurable.

39. Milestone M1 – Android MVP

M1 should include:

- Authentication.

- family.

- child.

- pairing.

- device identity.

- device health.

- Usage Access.

- screen time.

- app rules.

- schedules.

- requests.

- Web Safety foundation.

- notifications.

- offline policy.

40. M1 Acceptance Rule

Payment/acceptance should require:

- Feature ID checklist.

- demo.

- QA results.

- source code pushed to Druvatara repository.

- known limitations.

- no unresolved Critical defects.

41. Phase 3 – Android Commercial Features

After M1, add:

- Location.

- safe zones.

- reports.

- Safety Score.

- TARA.

- co-parent.

- subscriptions.

- privacy.

- support.

- admin.

42. Sprint 11 – Reports and Safety Score

Scope:

- Weekly report.

- report worker.

- report sections.

- Safety Score.

- factor explanations.

- completeness.

43. Safety Score Gate

Must verify:

- deterministic result.

- score 0–100.

- no missing-data-as-safe issue.

- factor explanation.

- versioning.

44. Sprint 12 – TARA

Scope:

- AI gateway.

- provider abstraction.

- parent chat.

- alert explanation.

- report summary.

- Safety Score explanation.

- feedback.

- guardrails.

45. TARA Acceptance Gate

Mandatory:

- cross-family security.

- context minimisation.

- structured output.

- provider timeout.

- hallucination checks.

- prompt injection tests.

- kill switch.

46. Sprint 13 – Co-Parent

Scope:

- Invitation.

- roles.

- approval permissions.

- location permission.

- revocation.

- audit.

47. Co-Parent Security Gate

Mandatory UAT:

Co-parent granted reports but NOT location

→ report works

→ location denied

Location later granted

→ works

Co-parent revoked

→ all access denied

48. Sprint 14 – Billing

Scope:

- Plans.

- Play Billing.

- entitlement service.

- verification.

- RTDN.

- device limits.

- subscription state.

- restore.

- grace.

49. Billing Gate

No acceptance until:

- client cannot self-grant premium.

- backend verification works.

- duplicate purchase fails.

- restore works.

- expiry/recovery works.

50. Sprint 15 – Privacy and Support

Scope:

- Privacy dashboard.

- account deletion.

- child deletion.

- export.

- consent.

- support tickets.

- diagnostics.

51. Sprint 16 – Admin Portal

Scope:

- Admin auth.

- MFA.

- RBAC.

- family/device lookup.

- subscription.

- support.

- privacy requests.

- feature flags.

- audit.

52. Admin Security Gate

Mandatory:

- Support cannot access location.

- Finance cannot access child telemetry.

- product role cannot suspend account.

- lower roles receive 403.

- actions audit correctly.

53. Milestone M2 – Android Commercial Feature Complete

M2 means:

- All contracted P0/P1 functionality code complete.

- backend/admin complete.

- billing complete.

- privacy complete.

- TARA complete.

- QA started.

It does not mean production-ready yet.

54. Phase 4 – Android Beta and Hardening

Primary objective:

Find problems that feature-development demos will not reveal.

Focus:

- Real devices.

- OEMs.

- battery.

- VPN.

- offline.

- network switching.

- crashes.

- store policy.

- security.

55. Internal Alpha

Recommended participants:

- Founder.

- vendor team.

- QA.

- small trusted test group.

Environment:

Staging or closed testing.

56. Alpha Exit Criteria

- Main flows complete.

- no known cross-family defects.

- no repeated data corruption.

- screen-time reliable enough for external beta.

- pairing usable without developer intervention.

- crashes manageable.

57. Closed Android Beta

Recommended:

- 20–100 invited family testers initially.

- expand gradually.

Track:

- onboarding.

- permission completion.

- device health.

- OEM reliability.

- battery.

- VPN.

- support.

58. Beta Feedback Channels

Use:

- In-app feedback.

- support ticket.

- structured tester form.

- crash analytics.

Do not rely solely on WhatsApp messages to developers.

59. Beta Defect Triage

Daily/regular triage categories:

BLOCKER

CRITICAL

HIGH

MEDIUM

LOW

60. Critical Beta Defects

Examples:

- Cross-family data.

- wrong child policy.

- location disclosure.

- screen-time bypass widespread.

- subscription duplicate charging.

- child device unusable.

61. Android OEM Validation

Required device families:

- Samsung.

- Pixel.

- Xiaomi/Redmi.

- OnePlus.

- Vivo.

- OPPO/Realme.

- Motorola.

62. Battery Validation

Run:

- idle overnight.

- normal school-day usage.

- high-use day.

- VPN active.

- location active.

- poor network.

63. Security Validation

Required before commercial launch:

- API penetration test.

- mobile security review.

- admin security test.

- cross-family tests.

- token/session review.

- secret scan.

64. Privacy Validation

Required:

- Data inventory matches code.

- child privacy notice.

- location.

- deletion.

- export.

- co-parent.

- analytics exclusions.

- TARA data flow.

65. Play Compliance Validation

Required:

- Monitoring app classification.

- Data Safety.

- privacy policy.

- background location.

- VPN.

- package visibility.

- Accessibility if applicable.

- billing.

66. Milestone M3 – Android Release Candidate

A release candidate is created only when:

- Feature scope frozen.

- Critical defects = 0.

- High defects within approved threshold.

- security gate passed.

- privacy gate passed.

- store package ready.

67. Release Candidate Rule

The exact RC build tested must be the build submitted unless only controlled signing/store metadata changes occur.

No untested code added after RC acceptance.

68. Android Store Submission

Sequence:

Internal

→ Closed

→ Open/Production as applicable

→ Staged rollout

Exact Play process depends on account/policy status.

69. Android Staged Rollout

Recommended:

5%

→ 20%

→ 50%

→ 100%

subject to:

- Crash rates.

- ANRs.

- support.

- policy failures.

- security events.

70. Milestone M4 – Android Commercial Launch

M4 achieved when:

- Production backend active.

- production monitoring active.

- Play Store build approved/published.

- billing live.

- support ready.

- backups verified.

- rollback ready.

- documentation handed over.

71. iOS Strategy

iOS shall begin with feasibility confirmation rather than immediate full-feature coding.

This reduces risk from:

- Family Controls entitlement.

- Screen Time architecture.

- extension behaviour.

- App Review.

72. Phase 6 – iOS POC

Indicative: 2–4 sprints depending approvals.

POC goals:

- Family Controls.

- FamilyActivityPicker.

- Managed Settings.

- Device Activity.

- shield.

- child request architecture.

- Family Sharing.

73. iOS POC Acceptance Journey

Mandatory demonstration:

Family authorisation

→ select app

→ configure limit

→ activity threshold reached

→ shield

→ temporary approval

→ restored policy

74. iOS POC Gate

No full iOS commercial commitment until:

- entitlement route confirmed.

- POC works on real devices.

- extension architecture stable.

- platform limitations documented.

75. Milestone M5 – iOS Feasibility Approved

Outputs:

- POC build.

- technical report.

- entitlement status.

- final iOS feature matrix.

- updated estimate.

76. Phase 7 – iOS Commercial Development

Recommended sprint blocks:

iOS Sprint A

Account/family/shared Flutter integration.

iOS Sprint B

Family Controls setup.

iOS Sprint C

Screen Time and Managed Settings.

iOS Sprint D

Requests and schedules.

iOS Sprint E

Location/geofence.

iOS Sprint F

Reports/TARA/Safety Score.

iOS Sprint G

Subscription/privacy.

iOS Sprint H

Hardening/App Store.

77. Shared Flutter Strategy

Shared code should be reused for:

- Authentication.

- parent UI.

- family.

- reports.

- TARA.

- subscription UI.

- account settings.

Native Swift handles:

- Family Controls.

- Managed Settings.

- Device Activity.

- extensions.

- platform-specific location.

78. iOS Beta

Use:

- Internal TestFlight.

- external TestFlight when ready.

Test:

- Family Sharing.

- authorisation.

- revocation.

- extension lifecycle.

- app termination.

- location.

- StoreKit.

79. iOS Security and Privacy Gate

Same core backend/security requirements as Android plus:

- Keychain.

- App Groups.

- entitlement correctness.

- Apple token privacy.

- extension access controls.

80. Milestone M6 – iOS Release Candidate

Requirements:

- iOS contracted Feature IDs complete.

- entitlement proven.

- TestFlight UAT passes.

- App Privacy complete.

- account deletion works.

- StoreKit verified.

81. Milestone M7 – iOS Commercial Launch

Achieved when:

- App Store approval.

- production backend integration.

- iOS monitoring.

- subscription.

- support.

- store metadata.

- handover.

82. Phase 9 – Stabilisation

After launch:

- Fix launch defects.

- monitor crashes.

- monitor device health.

- improve onboarding.

- update OEM/iOS guidance.

83. Warranty Period

Vendor proposal shall specify warranty.

Recommended procurement expectation:

30–90 days after accepted production launch, depending contract.

Warranty covers defects in contracted functionality, not new scope.

84. Warranty Defect Definition

A defect is:

- Delivered functionality does not meet approved requirement/use case.

Not:

- New feature request.

- later product change.

- third-party policy change requiring new architecture unless contract includes maintenance.

85. Post-Launch Maintenance

Separate agreement may cover:

- OS compatibility.

- store updates.

- security patches.

- SDK updates.

- backend maintenance.

- monitoring.

- incident support.

86. RACI Definitions

R – Responsible

Performs the work.

A – Accountable

Final owner/approver.

C – Consulted

Provides required input.

I – Informed

Kept informed.

87. RACI Roles

Abbreviations:

FND = Founder/Product Owner

PM = Vendor Project Manager

UX = UI/UX

AND = Android

IOS = iOS

BE = Backend

AI = AI

QA = QA

SEC = Security

PRV = Privacy/Compliance

DO = DevOps

88. High-Level RACI

| Activity | FND | PM | UX | AND | IOS | BE | AI | QA | SEC | PRV | DO |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Product scope | A | R | C | C | C | C | C | C | C | C | I |
| UI/UX | A | C | R | C | C | C | C | C | C | C | I |
| Android | A | C | C | R | I | C | I | C | C | C | C |
| iOS | A | C | C | I | R | C | I | C | C | C | C |
| Backend | A | C | I | C | C | R | C | C | C | C | C |
| TARA | A | C | C | I | I | C | R | C | C | C | C |
| QA | A | C | C | C | C | C | C | R | C | C | I |
| Security | A | C | I | C | C | C | C | C | R | C | C |
| Privacy | A | C | C | C | C | C | C | C | C | R | I |
| DevOps | A | C | I | C | C | C | C | I | C | C | R |
| UAT | A/R | C | I | C | C | C | C | R | C | C | I |
| Store launch | A | R | C | R | R | C | I | C | C | C | C |

89. Founder Responsibilities

Founder/Product Owner shall:

- Approve scope.

- approve design.

- resolve product decisions.

- approve milestones.

- control Druvatara accounts.

- approve commercial pricing.

- approve launch.

- manage scope changes.

90. Vendor Project Manager Responsibilities

Vendor PM shall:

- Maintain sprint plan.

- track dependencies.

- run status meetings.

- maintain risk log.

- track defects.

- prepare demos.

- maintain delivery evidence.

91. Engineering Lead Responsibilities

Each lead shall:

- Own implementation quality.

- code review.

- technical decisions.

- documentation.

- test readiness.

- integration.

92. QA Responsibilities

QA shall:

- Build test plan.

- execute tests.

- maintain defect register.

- verify real devices.

- prepare UAT.

- produce evidence.

93. Security Responsibilities

Security reviewer shall:

- Threat review.

- security architecture review.

- penetration-test coordination.

- admin/security testing.

- release gate.

94. Privacy Responsibilities

Privacy reviewer shall:

- Permission review.

- data-flow review.

- location.

- child notice.

- consent.

- retention.

- deletion.

- processors.

- TARA privacy.

95. DevOps Responsibilities

DevOps shall:

- Environments.

- CI/CD.

- secrets.

- monitoring.

- backups.

- deployments.

- rollback.

- production access.

96. Project Governance Meetings

Recommended:

Weekly Programme Review

Participants:

- Founder/Product.

- PM.

- technical leads.

- QA.

Sprint Planning

Every sprint.

Sprint Demo

Every sprint.

Defect Review

During beta/hardening.

Security/Privacy Gate

At defined milestones.

97. Weekly Status Report

Vendor provides:

Completed

In Progress

Next

Blocked

Risks

Decisions Needed

Defect Summary

Budget/Change Status

98. Sprint Demo Rule

Only working software demonstrated against approved environment counts.

Slides/screenshots alone do not constitute feature completion.

99. Development Evidence

Every sprint should link:

- Feature IDs.

- pull requests.

- build.

- tests.

- demo.

- defects.

100. Backlog Structure

Recommended hierarchy:

EPIC

↓

FEATURE ID

↓

USER STORY

↓

TASK

↓

TEST CASE

101. Jira/Project Tool Naming

Example:

Feature:

ST-001 Daily Screen-Time Limit

Story:

ST-001-US-01 Parent configures daily limit

Task:

ANDROID-ST-001-LOCAL-ENFORCEMENT

102. Definition of Ready

Story enters development only if:

- requirement clear.

- acceptance criteria exist.

- design available where required.

- dependencies known.

- API/data needs identified.

103. Definition of Done

Story is Done only if:

- code complete.

- peer reviewed.

- automated tests.

- QA tested.

- error state.

- offline state where applicable.

- analytics.

- docs.

- acceptance criteria pass.

104. Milestone Acceptance

Each milestone shall have a signed acceptance note.

Example:

Milestone: M1 Android MVP

Build:

Date:

Features Accepted:

Features Conditional:

Defects:

Payment Approved:

Approved By:

105. Commercial Payment Strategy

Recommended procurement model:

Avoid paying 100% upfront.

Example structure:

- Mobilisation payment.

- milestone payments.

- store-launch payment.

- final handover retention.

Exact percentages should be negotiated.

106. Recommended Payment Principle

Payment should follow verified deliverables, not elapsed calendar time alone.

107. Example Milestone Payment Logic

Illustrative only:

10% mobilisation

20% foundation

20% Android MVP

20% Android commercial RC

10% Android launch

10% iOS milestone

10% final handover

Actual commercial structure shall be negotiated.

108. Retention Payment

Consider retaining final:

5–10%

until:

- source handover.

- credential handover.

- documentation.

- unresolved high defects closed.

- production access transferred.

Commercial decision only.

109. Change Request Process

Any new scope requires:

CR ID

Requested Feature

Reason

Feature IDs

Cost

Timeline Impact

Architecture Impact

Security/Privacy Impact

Approval

110. Change Approval

No vendor may implement billable new scope based only on informal conversation.

Founder/Product approval required.

111. Scope Clarification vs Change

Clarification

Existing Feature ID already implies behaviour.

Change

New capability not in contracted baseline.

Disputes resolved using:

- Feature Catalogue.

- Use Cases.

- SRS.

- signed quotation.

112. Technical Decision Record

Major architecture changes require ADR.

Examples:

- Switch database.

- replace Flutter.

- introduce Accessibility.

- use new AI provider.

- introduce microservices.

- change billing architecture.

113. ADR Contents

ADR ID

Decision

Context

Options

Selected Option

Reason

Risks

Consequences

Approvers

114. Risk Register

Every programme shall maintain:

| Risk | Probability | Impact | Owner | Mitigation | Status |
| --- | --- | --- | --- | --- | --- |

115. Key Project Risks

Major risks include:

- Android policy/store rejection.

- OEM reliability.

- iOS Family Controls entitlement delay.

- iOS capability limitation.

- aggressive scope growth.

- insufficient real-device testing.

- security defects.

- billing complexity.

- AI cost or safety issues.

- vendor lock-in.

- production-account ownership.

- low budget creating under-resourcing.

116. Android Store Risk Mitigation

Mitigate through:

- Early policy review.

- VPN POC.

- permission minimisation.

- monitoring-tool declaration.

- clear disclosures.

117. iOS Risk Mitigation

Mitigate through:

- entitlement request early.

- iOS POC before full build.

- native Swift specialist.

- platform-honest scope.

118. OEM Risk Mitigation

Mitigate through:

- real-device matrix.

- battery tests.

- manufacturer guidance.

- health-state transparency.

119. Scope Risk Mitigation

Use:

- Feature IDs.

- signed baseline.

- change requests.

- P0/P1 discipline.

120. Security Risk Mitigation

Use:

- code review.

- SAST.

- dependency scanning.

- penetration test.

- least privilege.

- security gate.

121. Vendor Dependency Risk

Mitigate by requiring:

- Druvatara Git repositories.

- Druvatara cloud accounts.

- Druvatara store accounts.

- documentation.

- no hidden proprietary backend.

122. Project Blockers

A blocker is an issue that prevents meaningful continuation of dependent work.

Examples:

- Family Controls entitlement denied.

- unavailable Apple developer access.

- backend credentials unavailable.

- design not approved.

- store-policy rejection requiring architecture change.

123. Blocker Escalation

Vendor must report blocker immediately in project tracker.

Each blocker has:

- owner.

- date.

- impact.

- next action.

124. No Silent Blockers

Vendor shall not allow blocked work to remain hidden until milestone date.

125. Dependency Management

Major dependencies:

Authentication → Family

Family → Child

Child → Pairing

Pairing → Device

Device → Policy

Policy → Screen Time / Apps / Web

Data → Reports / Score

Score + Alerts → TARA

Subscription → Commercial Entitlement

126. Parallel Work

Can proceed concurrently:

- UX.

- backend.

- Flutter.

- Android native.

- DevOps.

But integration checkpoints are mandatory.

127. Integration Sprint Rule

At least every 1–2 sprints, teams integrate into one working end-to-end environment.

Do not allow:

- Backend "finished separately."

- mobile "finished separately."

until final month.

128. Environment Promotion

DEV

↓

QA

↓

STAGING

↓

PRODUCTION

No direct developer-to-production deployment.

129. Build Number Discipline

Every test/demo references:

- App version.

- build number.

- backend version.

- environment.

130. Release Branching

Use approved Git strategy.

Release candidates are tagged.

Example:

guardian-android-v1.0.0-rc1

backend-v1.0.0-rc1

131. QA Entry Criteria

A feature enters QA when:

- Developer tests complete.

- no known blocker.

- build deployed.

- test data available.

- acceptance criteria documented.

132. QA Exit Criteria

- Mandatory cases pass.

- defects logged.

- blocker/critical resolved.

- regression executed where required.

133. UAT Entry Criteria

- QA passed.

- security/privacy gates passed for relevant features.

- near-production build.

- test accounts prepared.

134. UAT Participants

Recommended:

- Founder.

- internal tester.

- selected trusted users.

- QA facilitator.

Vendor developers should support but not self-approve UAT.

135. UAT Scope

Use the 17 mandatory scenarios defined in QA-008 and USECASE-019, including:

- first-time setup.

- Android protection.

- Web Safety.

- location.

- co-parent.

- offline.

- iOS Screen Time.

- TARA.

- subscription.

- deletion.

- tenant isolation.

136. UAT Failure

Failed Critical/High journey normally blocks release.

Waivers require documented Founder/Product acceptance and must not override security/privacy absolute blockers.

137. Security Release Gate

Production launch blocked if:

- Critical vulnerability open.

- unresolved cross-family defect.

- authentication bypass.

- known production secret exposure.

138. Privacy Release Gate

Blocked if:

- Location accessible improperly.

- deletion broken.

- Privacy Policy materially inaccurate.

- child data goes to unapproved analytics/provider.

- co-parent access broken.

139. Store Release Gate

Blocked if:

- required declaration absent.

- Data Safety/App Privacy inconsistent.

- entitlement missing.

- reviewer flow unusable.

140. Production Readiness Review

Before launch review:

Product

Engineering

QA

Security

Privacy

DevOps

Billing

Store

Support

Documentation

141. Android Launch Checklist

[ ] RC signed

[ ] Security passed

[ ] Privacy passed

[ ] Backup verified

[ ] Monitoring active

[ ] Billing production ready

[ ] FCM production ready

[ ] Play declarations complete

[ ] Privacy Policy live

[ ] Terms live

[ ] Support ready

[ ] Rollback ready

142. iOS Launch Checklist

[ ] Family Controls entitlement

[ ] TestFlight UAT

[ ] App Privacy

[ ] StoreKit

[ ] Account deletion

[ ] Review credentials

[ ] Extension signing

[ ] Production monitoring

[ ] Security/privacy gates

143. Launch Day Roles

Founder

Go/no-go.

Vendor PM

Coordination.

Engineering

Deployment.

QA

Smoke testing.

DevOps

Monitoring/rollback.

Support

Customer response.

144. Launch Smoke Test

Immediately verify:

- Login.

- family load.

- pairing.

- policy sync.

- child heartbeat.

- request.

- push.

- billing.

- TARA.

- admin.

- location where enabled.

145. Rollback Authority

DevOps lead + technical lead, under launch/incident authority.

Do not delay rollback merely to protect perception of launch success.

146. Post-Launch Hypercare

Initial launch period shall include increased:

- monitoring.

- defect review.

- support review.

- crash analysis.

- billing reconciliation.

147. Support Handover Before Launch

Support receives:

- FAQ.

- permission guides.

- device-health codes.

- subscription guide.

- escalation matrix.

148. Documentation Handover

Each workstream shall maintain docs continuously, not at project end only.

149. Required Technical Documentation

Vendor must deliver:

- Architecture.

- API.

- DB.

- setup.

- deployment.

- mobile build.

- provider integrations.

- admin.

- billing.

- TARA.

- troubleshooting.

150. Source Code Ownership

All custom Guardian source code commissioned under the final agreement shall be transferred/licensed according to Druvatara-approved IP terms.

Preferred:

Druvatara owns the commissioned product source code.

151. Repository Ownership

Repositories shall be created in Druvatara-controlled organisation/account from the beginning where possible.

152. Cloud Ownership

Production cloud account:

Druvatara-owned

not vendor personal/company account where this would create lock-in.

153. Store Ownership

Druvatara owns:

- Google Play Console.

- Apple Developer.

- App Store Connect.

154. Provider Ownership

Druvatara controls:

- Firebase.

- AI provider.

- map provider.

- email provider.

- payment/store backend access.

- threat intelligence.

155. Credential Handover

Vendor must not retain production credentials after termination unless explicitly authorised for maintenance.

156. Final Handover Checklist

[ ] Source

[ ] Git ownership

[ ] Cloud

[ ] DNS

[ ] Firebase

[ ] Play

[ ] Apple

[ ] AI

[ ] Maps

[ ] Email

[ ] Billing

[ ] Monitoring

[ ] Backups

[ ] Documentation

[ ] Admin accounts

[ ] Secrets inventory

[ ] Support docs

[ ] Known issues

157. Knowledge Transfer

Vendor shall conduct handover sessions covering:

- Architecture.

- backend.

- Android.

- iOS.

- deployment.

- database.

- admin.

- billing.

- TARA.

- troubleshooting.

158. Recorded Handover

Where contract permits, technical handover sessions should be recorded and stored in Druvatara-controlled storage.

159. Known Issues Register

At final acceptance, vendor provides:

Issue

Severity

Affected Version

Workaround

Planned Fix

Owner

No hidden defects.

160. Final Acceptance

Final project acceptance occurs only after:

- Contracted Feature IDs accepted.

- production builds released.

- critical/high agreed defects closed.

- source code delivered.

- accounts transferred.

- documentation complete.

- backups validated.

- monitoring visible.

- handover complete.

161. Final Acceptance Does Not Mean Product Ends

After v1:

- OS updates.

- policy changes.

- security patches.

- user feedback.

will require ongoing product maintenance.

162. Project Metrics

Track:

- Sprint velocity.

- Feature completion.

- defect rate.

- reopen rate.

- test pass rate.

- build success.

- milestone variance.

- escaped defects.

Do not optimise velocity at expense of safety.

163. Quality Metric

Better than:

Number of tickets closed

is:

Accepted Feature IDs without reopened high-severity defects.

164. Vendor Performance Metrics

May include:

- Milestone delivery.

- defect leakage.

- documentation.

- response.

- code quality.

- handover completeness.

165. Delay Management

When schedule slips:

Vendor shall provide:

- Cause.

- affected milestone.

- dependencies.

- revised plan.

- mitigation.

Not simply:

“Development is taking longer.”

166. Budget Tracking

Vendor reports:

- Contracted amount.

- approved change requests.

- invoices.

- remaining milestone payments.

- third-party costs.

167. Third-Party Cost Register

Must separately track:

- Cloud.

- AI.

- maps.

- SMS/email.

- threat intelligence.

- monitoring.

- Apple/Google developer fees where applicable.

168. Licence Cost Ownership

Vendor quotation shall distinguish:

ONE-TIME DEVELOPMENT COST

RECURRING PLATFORM COST

USAGE-BASED COST

STORE FEE

MAINTENANCE COST

169. Founder Decision Log

Maintain decisions such as:

- pricing.

- location phase.

- device limit.

- TARA provider.

- subscription tiers.

- Android permission choice.

This reduces repeated debate.

170. Open Decision Escalation

Vendor submits:

Decision Needed

Options

Recommendation

Cost

Schedule Impact

Deadline

Founder/Product resolves.

171. Project Communication Rule

Critical technical/commercial decisions shall not exist only in chat messages.

They must be reflected in:

- ticket.

- decision log.

- specification.

- change request.

172. Intellectual Property Control

Contract should address:

- custom code.

- designs.

- prompts.

- database schema.

- deployment scripts.

- documentation.

- generated assets.

Third-party OSS remains subject to its license.

173. No Hidden Proprietary Dependency

Vendor shall disclose any proprietary component without which Druvatara cannot run the system.

Druvatara must approve before use.

174. Vendor Subcontractors

Vendor shall disclose:

- Subcontractor.

- role.

- access.

- data exposure.

No undisclosed subcontractor receives production child data.

175. Development Data Rule

Development should use:

- synthetic data.

- test families.

- test devices.

Production child data shall not be copied into development environments.

176. Security During Development

Required:

- Branch protection.

- MFA.

- secrets management.

- no credentials in repo.

- vulnerability scanning.

177. Code Review

No critical production code directly committed to main without review except tightly controlled emergency procedure.

178. Release Approval Authority

Production release requires Druvatara-authorised approval.

Vendor cannot independently publish a release merely because sprint is complete.

179. App Store Credentials

Vendor may upload builds through delegated role.

Founder/Druvatara retains account control.

180. Store Rejection Process

If rejected:

- Record reason.

- map to policy.

- determine code/metadata change.

- test.

- resubmit.

- retain evidence.

No deceptive workaround.

181. Project Completion Status

A feature may be:

NOT STARTED

DESIGN

DEVELOPMENT

CODE COMPLETE

QA

UAT

ACCEPTED

RELEASED

BLOCKED

DEFERRED

182. Overall Programme Dashboard

Recommended columns:

| Workstream | Planned | Actual | Status | Risk | Owner |
| --- | --- | --- | --- | --- | --- |

183. Milestone Summary

| Milestone | Outcome |
| --- | --- |
| M0 | Project mobilisation |
| M1 | Android MVP |
| M2 | Android commercial feature complete |
| M3 | Android release candidate |
| M4 | Android production launch |
| M5 | iOS POC approved |
| M6 | iOS release candidate |
| M7 | iOS production launch |
| M8 | Final stabilisation/handover |

184. M8 – Final Handover

Final programme milestone:

- Warranty transition.

- all documentation.

- access review.

- repository confirmation.

- credential handover.

- known issues.

- ownership signoff.

185. Project Acceptance Matrix

| Area | Acceptance Owner |
| --- | --- |
| Product | Founder/Product Owner |
| Android | Product + QA |
| iOS | Product + QA |
| Backend | Technical/Product |
| Security | Security Reviewer |
| Privacy | Privacy Reviewer |
| Billing | Product/Finance |
| DevOps | Technical/Operations |
| Store | Product |
| Final Handover | Founder |

186. No Partial Acceptance by Assumption

If a feature is:

- not tested.

- unsupported.

- mocked.

- only partially integrated.

It must be recorded accordingly.

Not:

Completed

187. Recommended Vendor Quotation Structure

Druvatara should ask vendors to quote:

Package 1

Product/UX + Foundation.

Package 2

Android MVP.

Package 3

Android Commercial.

Package 4

Backend/Admin/TARA.

Package 5

Android QA/Security/Launch.

Package 6

iOS POC.

Package 7

iOS Commercial.

Package 8

Handover/Maintenance.

188. Vendor Timeline Response Format

Vendor shall return:

| Phase | Start | End | Sprints | Team | Dependencies |
| --- | --- | --- | --- | --- | --- |

189. Vendor Estimate Confidence

For uncertain features classify:

HIGH CONFIDENCE

MEDIUM CONFIDENCE

POC REQUIRED

STORE DEPENDENT

ENTITLEMENT DEPENDENT

190. Android Critical POCs

Must identify early:

- Consumer app control.

- VPN.

- package visibility.

- OEM background.

- Accessibility if considered.

191. iOS Critical POCs

Must identify early:

- Family Controls.

- Managed Settings.

- Device Activity.

- Shield actions.

- child request integration.

192. Advanced AI Workstreams

Not part of core programme:

- Grooming.

- sextortion.

- self-harm.

- sensitive media.

These require separate project charter.

193. Future UEM Programme

Druvatara UEM shall have a separate:

- BRD.

- PRD.

- architecture.

- implementation programme.

Do not silently expand Guardian contract into enterprise UEM.

194. Project Risk Acceptance

Critical unresolved risk cannot be accepted merely to preserve schedule.

Example:

- cross-family access.

Release must slip rather than knowingly ship it.

195. Cost vs Scope Decision Rule

If budget pressure occurs, reduce:

- feature scope.

- release breadth.

- advanced P1/P2.

Do not reduce:

- authentication security.

- family isolation.

- privacy.

- basic QA.

- source ownership.

- backup.

- error handling.

196. MVP Reduction Order

If necessary, defer in approximately this order:

- Advanced TARA.

- advanced analytics.

- location history.

- monthly reports.

- multilingual.

- advanced notification preferences.

- advanced admin dashboards.

Protect:

- auth.

- pairing.

- policy.

- screen time.

- device health.

- offline.

- security.

197. Quality-First Contract Principle

Druvatara should avoid contracts rewarding only:

Screens completed

or:

Percentage development completed

without acceptance criteria.

Use working Feature IDs and milestones.

198. Final Execution Principle

The programme should behave as:

REQUIREMENT

↓

DESIGN

↓

IMPLEMENT

↓

TEST

↓

DEMONSTRATE

↓

ACCEPT

↓

PAY

↓

RELEASE

rather than:

PAY

↓

BUILD EVERYTHING

↓

DISCOVER PROBLEMS AT END

199. Acceptance Criteria for PROJECT-025

This document shall be operationally approved once:

- Scope baseline accepted.

- phases accepted.

- sprint cadence accepted.

- RACI agreed.

- milestones linked to Feature IDs.

- acceptance owners named.

- payment gates agreed.

- POC gates agreed.

- security/privacy gates agreed.

- UAT model approved.

- handover requirements included in contract.

200. Development Company Deliverables

The selected vendor shall return:

Project Plan

- Detailed Gantt/timeline.

- sprint schedule.

- dependencies.

- resources.

Backlog

- Feature IDs.

- user stories.

- estimates.

- sprint assignments.

RACI

- Named persons.

Milestone Plan

- Deliverables.

- acceptance.

- payment.

Risk Register

- technical.

- commercial.

- store.

- security.

Release Plan

- Alpha.

- beta.

- RC.

- production.

Handover Plan

- code.

- infrastructure.

- accounts.

- documentation.

201. Open Project Decisions

The following require Founder/vendor agreement before contract start:

- Vendor/team selection.

- final budget.

- fixed-price vs time-and-materials.

- payment percentages.

- sprint length.

- Android MVP exact Feature IDs.

- location phase.

- TARA commercial-launch scope.

- subscription tier strategy.

- admin P0/P1 split.

- Android device test matrix.

- beta tester count.

- warranty duration.

- maintenance agreement.

- iOS POC timing.

- iOS production start gate.

- external security test vendor.

- privacy/legal reviewer.

- project management tool.

- source repository organisation.

- cloud provider.

- analytics provider.

- AI provider.

- map provider.

- threat provider.

- support tooling.

- release sign-off authority.

- change-request authority.

- escalation cadence.

- final handover payment retention.

202. Conclusion

This Project Implementation Plan establishes how Druvatara Guardian shall move from specification to production.

The project shall not be treated as:

“Build a parental control app.”

It is a coordinated delivery programme involving:

MOBILE

+

NATIVE DEVICE CONTROL

+

BACKEND

+

DATABASE

+

SECURITY

+

PRIVACY

+

AI

+

BILLING

+

ADMIN

+

DEVOPS

+

QA

+

STORE COMPLIANCE

The Android-first strategy reduces execution risk by allowing Druvatara to validate:

- Pairing.

- screen time.

- app controls.

- Web Safety.

- device reliability.

- backend.

- billing.

- TARA.

- support.

before expanding fully into iOS.

The iOS programme shall begin with a dedicated Family Controls/Screen Time proof of concept before full commercial implementation.

The most important procurement rule is:

Druvatara shall pay for accepted milestones tied to working Feature IDs and evidence—not simply for elapsed development time or screenshots.

The most important quality rule is:

No milestone is complete until the applicable implementation, error handling, offline behaviour, security, privacy, testing and documentation are delivered.

The most important ownership rule is:

Repositories, production accounts, cloud infrastructure, store accounts, provider accounts, signing assets and product documentation must remain under Druvatara's control.

And the final programme rule is:

If budget, schedule and quality conflict, Druvatara should reduce scope before reducing security, privacy, reliability or ownership controls.

End of Document

Document ID: DT-GUARDIAN-PROJECT-025
Version: 1.0
Classification: Strictly Confidential and Proprietary
Copyright: Druvatara